## Sheet1
Components:	########	K8S CLUSTER	########	Time requirements	########	BACKEND	########	Time requirements	########	FRONTEND	########	Time requirements	########	CONSUMERS	########	Time requirements
				(in days)				(in days)				(in days)				(in days)
	1) cluster creation			1	1) communication with k8s API			2	1) login (authentication flow)			1	1) communication with backend			1
					-testing yaml files vs kubectl commands
	2) assigning roles and permissions			1					2) rabbitmw server creation			1	2) functional specifications			2
					2) frontend authentication API			2					-topics
* Για τον υπολογισμό των χρονικών απαιτήσεων θεωρώ ότι έχω 4 μέρες τη βδομάδα διαθέσιμες για τη διπλωματική.	3) DB Pod creation			3	-communication with DB (Pod 2) and authentication of users				3) producing credentials and creating vhosts			1	-type
	-schema – model design for authn/authz												-exchanges
	-schema – model design for consumer data				3) rabbitmq server creation API			2	4) URL to rabbimq management UI			1	-etc
	-persistent volumes + persistent volume claims				-k8s replication > # of Pod 1 replicas
	-communication with other pods + ports				-credentials and vhosts implementation				5) consumer creation			1
	-communication with backend + ports								-topics, type, exchange details
** Αυτές οι 4 μέρες προκύπτουν από 2 μέρες δουλειάς Δευτέρα – Παρασκευή και άλλες 2 μέρες δουλειάς Σάββατο – Κυριακή					4) URL to rabbitmq management UI API			1
					-providing access to the management UI through an Ingress

					5) consumer creation			2
					-Pod 3 with consumer process
					-testing 1 central Pod 3 with multiple processes vs many small differentiated consumer pods

Total Time Requirement:					6) resources owned by user and their state API			2
24	days			5				11				5				3
or
6	weeks

*** Δεν έχω ξανακάνει εκτίμηση χρόνου σε έργο ανάπτυξης λογισμικού, αλλά έχω την εντύπωση ότι ήμουν αρκετά συντηρητικός με τον χρόνο που έδωσα στο κάθε task.
**** Βασικά το έκανα έτσι ώστε να χωρέσει στον 1 μιση μήνα που έχω διαθέσιμο μέχρι να χρειαστεί να ασχοληθώ με το DSL κομμάτι της διπλωματικής.